## Slide 1
DRAFT: SLS Annual Assembly 2026 - Event Info (1/2)
Main Information |  |  | 
Event Name | SLS Annual Assembly 2026 | Event Sponsor | [TBC - Leadership Track]
Track Name | Leadership | Event User | SLS / Leadership Track
Program | SLS | Event Manager | [TBC - EMU]
Milestone in Project Charter? | Yes | Location | City Hub (proposed)
Interdependent Events / Programs | Fellowship & 2030 Leaders | # of Attendees | 300 (venue capacity)
Event Access | Private - invitation only | Partcipent Numbers | 300 SLS members
 |  | Filtration Required? | Yes
Event Description
One-evening annual assembly for the full SLS membership. No graduation segment in 2026. Members convene at City Hub for four hours: the year's achievements shown and told by the members who delivered them, recognition of the partners, Council members, Chapter teams and contributors behind them, and the direction for 2027. Venue capacity is 300.
Overall Budget |  |  | 
Budget Sub-category | Project Code & Sub-category | Amount (pre-VAT) | Total Budget (pre-VAT)
Logistics | [Cost centre TBC] | SAR TBC | SAR TBC
Events Management | [Cost centre TBC] | SAR TBC | 
Program Delivery / Content | [Cost centre TBC] | SAR TBC | 
Timeline |  |  |  |  | 
Project Start Date | 20/09/2026 | Go Live Dates & Time | 12/12/2026 6:30 - 10:30 PM | Project End Date | 14/01/2027
Build Start Date | 09/12/2026 |  | Dismantle End Date | 13/12/2026 | 
Event Objective
Close the SLS year by showing what the society achieved and naming the people who achieved it. Members should leave able to name three things SLS delivered in 2026, having seen their own contribution acknowledged, and knowing what 2027 asks of them. Benchmarks to beat: satisfaction of 85% or better (2024: 77%) and 85% of confirmed guests attending (2024: 320 of 468).
Event Scope of Work
Venue: City Hub - site survey and layout for 300 across stage, seating and networking areas Agency: full pre-production, on-site delivery, dismantle and closeout Stage and set: stage and seating for 300, Year in Review gallery at the entrance Production: LED, sound, lighting, screen content, show-calling, standby power Content: three member stories, key messages, scripts, speaker and moderator briefing Recognition: Wall of the Year, nominations with the RSVP, citations, letters to employers Program: run of show, Isha inside the arrival window, one floor break mid-evening Registration: online sign-up, digital badge, RSVP cap and waitlist, 48-hour reconfirmation Guest experience: protocol, seating, signage and wayfinding, valet, parking, accessibility F&B: dinner scaled to reconfirmed numbers, staged release Support: translation, photography, videography, cleaning, H&S, medical and security Post-event: attendee survey and post-event report
* Events without approved event charters will not be approved on the event system
** Events without correct budgets allocated in the correct cost center and event management sub-category will not be approved on the event system
*** Event tier will be determined based on scoring criteria to determine the level of engagement from EMU
Filled by track
Collaborative, initially filled by track
Filled by events

## Slide 2
DRAFT: SLS Annual Assembly 2026 - Event Info (2/2)
Event Stakeholders |  |  | 
Internal |  | External | 
Track / Department name | Name and Role | Entity Name | Name and Role
Leadership Track Events (EMU) Procurement/Legal | [TBC] - Sponsor [TBC] - Manager [TBC] - Contracts | City Hub Event agency (RFP) | [TBC] - Venue ops [TBC] - Delivery
Project Timeline |  |  |  | 
# | Workstream/Phase | Main Deliverables | Start Date | End Date
1 | Initiation | Approved event charter and PO issued | 20/09/2026 | 15/10/2026
2 | Planning | Venue contract, agency award, run of show, achievements and citations | 18/10/2026 | 19/11/2026
3 | Execution | Invitations, registration and digital badges Build, stage, gallery and rehearsal Event day delivery and dismantle | 22/11/2026 09/12/2026 12/12/2026 | 10/12/2026 11/12/2026 13/12/2026
4 | Closure | Post-event report, survey results and vendor closeout | 14/12/2026 | 14/01/2027
Main Risks and Issues |  |  |  | 
Main Risks/Issues |  | Severity | Mitigation | Owner
 | 300 seats against a full-membership invitation. |  | Phased RSVP with a waitlist; seating and dinner to a 48-hour reconfirmed count. | Track / EMU
 | Achievements and citations not collected in time to build content. |  | One collection request to Chapter leads and the Council, due 19/11 with planning. | Leadership Track
R
Severity:
Low
Medium
High
Risk
Issue
R
Level of Attendees |  |  |  | 
Royal Highness, Highnesses and Excellencies | Key CEOs | Partners | Beneficiaries | Public
CEO / DCEO Required? | 
CEO | DCEO
Filled by track
Collaborative, initially filled by track
Filled by events
Events Comments
N/A
R